## 1. 72-Hour Countdown
Step 1: The 72-Hour Storm Countdown
The Restaurant Owner Hub · free tool
Print this the day a storm enters the forecast cone. Put initials in Owner and anything in Done. Completion updates automatically.
Window | Action | Owner | Done? | Why it matters
5-7 days | Call your agent: confirm spoilage, business interruption, and flood coverage |  |  | Coverage cannot be added once a storm is named
5-7 days | Withdraw cash for post-storm payroll and emergency purchases |  |  | Card networks and ATMs go down with the power
5-7 days | Test the generator and fill fuel cans |  |  | A generator you have not run in a year will not start
72 hours | Cancel or cut standing vendor orders |  |  | Product delivered before landfall is pure loss
72 hours | Photograph the full building, dining room, and every cooler and freezer |  |  | The before photos are the backbone of the claim
72 hours | Record walk-in, reach-in, and freezer temperatures and time-stamp them |  |  | Your baseline temperature evidence
72 hours | Place a max/min thermometer in every refrigerated unit |  |  | Proves whether product ever crossed 41F
48 hours | Run specials to sell down fresh protein and produce |  |  | Every case sold is a case you do not claim
48 hours | Consolidate frozen product into one packed freezer; shut the other off |  |  | A full freezer holds temperature roughly twice as long
48 hours | Freeze water jugs to fill empty freezer space |  |  | Free thermal mass now, drinking water later
48 hours | Send the team the written closure and pay plan |  |  | Staff who feel abandoned do not come back
48 hours | Confirm the emergency contact tree and group text thread |  |  | One person besides you must reach everyone
24 hours | Export sales, payroll, vendor list, and insurance policy off-site |  |  | Local-only records drown with the building
24 hours | Board or shutter glass; sandbag doors |  |  | Wind-driven water causes most restaurant storm loss
24 hours | Bring in all patio furniture, umbrellas, and signage |  |  | Loose items become projectiles and liability
24 hours | Raise POS terminals, printers, and low equipment off the floor |  |  | Six inches of water destroys undercounter units
24 hours | Unplug non-refrigeration equipment |  |  | Restoration surges kill electronics
12 hours | Shut off gas at the main; kill non-essential breakers |  |  | Fire and gas risk in an unattended building
12 hours | Leave refrigeration running and doors taped shut |  |  | Every hour of cold is product saved
12 hours | Last person out photographs the secured building and leaves |  |  | Proof you took reasonable precautions
Post-storm | Photograph and video everything BEFORE touching or discarding |  |  | No photo, no payment
Post-storm | Read max/min thermometers and log the peak temperature |  |  | Decides what must be discarded
Post-storm | Log every discarded item on sheet 3 before it goes in the dumpster |  |  | Adjusters will not pay for undocumented product
Post-storm | Notify your insurer and open the claim the same day |  |  | Most policies require prompt notice
Post-storm | Test hood, ansul, and compressors before firing any burner |  |  | Storm damage to safety systems is common
Post-storm | Check for boil-water notices; flush all water lines |  |  | Health departments check this first
Post-storm | Request re-inspection if required, then reopen on a short menu |  |  | Partial staff and inventory cannot run a full menu
COMPLETION |  |  |  | Type anything in the Done column to count it.
Keep your POS reporting in the cloud so a flooded terminal does not take your sales history with it. Cobblestone POS is free, no monthly fee: cobblestonepos.com

## 2. Cost of a Dark Day
Step 2: What Every Closed Day Actually Costs
The Restaurant Owner Hub · free tool
Fixed costs keep running whether or not you open. This tells you what you lose per dark day and where your break-even sits when you come back.
NORMAL TRADING
Average daily sales ($) | 4200
Food + beverage cost % | 30%
Variable labor % | 22% | Hourly staff only. Salaried managers belong in fixed costs below.
Other variable costs % (paper, cc fees, supplies) | 6%
Contribution margin %
Lost contribution per closed day ($)
FIXED COSTS THAT KEEP RUNNING (monthly)
Rent / CAM / property costs | 9500 | Due in full regardless of storm
Insurance premiums | 1400
Loan and equipment lease payments | 2100
Salaried management payroll | 11000 | Salaried exempt staff must be paid for any week they work
Utilities (base / standby) | 1800 | Still metered while you are dark
Software, POS, and subscriptions | 600 | A free POS makes this line smaller
Other fixed (accounting, licenses, security) | 700
Total monthly fixed cost ($)
Fixed cost per calendar day ($)
THE DAMAGE
TOTAL COST OF ONE CLOSED DAY ($) |  | Lost contribution plus fixed costs that ran anyway.
Days closed (estimate) | 5
TOTAL CLOSURE COST ($)
Storm prep spend (boards, fuel, ice, labor) ($) | 1800
Post-storm cleanup and restocking ($) | 3500
ALL-IN STORM COST BEFORE INSURANCE ($)
Compare this number to your business interruption deductible and waiting period. If the waiting period is 72 hours, the first three days are on you no matter what.

## 3. Food Loss Claim Log
Step 3: Claim-Ready Food Loss Log
The Restaurant Owner Hub · free tool
Fill one row per item BEFORE it goes in the dumpster. Photograph each unit first. Adjusters pay for documented product at cost, not menu price.
Date of loss |  |  | Claim / policy number
Storage unit | Item | Qty | Unit | Unit cost $ | Extended cost $ | Peak temp F | Photo file / note
Walk-in cooler
Walk-in cooler
Walk-in cooler
Walk-in cooler
Walk-in cooler
Walk-in cooler
Walk-in freezer
Walk-in freezer
Walk-in freezer
Walk-in freezer
Walk-in freezer
Walk-in freezer
Reach-in / line
Reach-in / line
Reach-in / line
Reach-in / line
Bar cooler
Bar cooler
Dry storage (water damage)
Dry storage (water damage)
TOTAL DOCUMENTED FOOD LOSS ($)
Line items logged
Items logged above 41F (must be discarded)
Cost, not menu price. Attach invoices for any high-value line. Keep the photos in a dated folder named to match column H.
Anything held above 41F for more than four hours goes out. When in doubt, throw it out - one foodborne illness costs more than the whole claim.

## 4. Claim Summary
Step 4: What You Can Actually Recover
The Restaurant Owner Hub · free tool
Pulls from the other sheets. Fill the yellow policy terms from your declarations page - not from memory.
LOSSES
Documented food loss ($)
Physical damage to property / equipment ($) | 0
Closure cost incl. prep & cleanup ($)
TOTAL LOSS ($)
POLICY TERMS
Spoilage coverage limit ($) | 25000
Spoilage deductible ($) | 1000 | Ask whether off-premises power failure is covered. Many policies exclude it by default.
Property deductible ($) | 5000
Business interruption waiting period (days) | 3
Days closed
Cost per closed day ($)
ESTIMATED RECOVERY
Spoilage recovery ($)
Property recovery ($)
Business interruption recovery ($) |  | Only days beyond the waiting period, and usually only when there is covered physical damage.
TOTAL ESTIMATED RECOVERY ($)
OUT OF POCKET AFTER INSURANCE ($)
% of the loss you absorb |  | Over 50% and your coverage is not doing the job. Fix it in the spring, not during the season.
Cash reserve on hand ($) | 20000
Reserve remaining after the storm ($) |  | Negative means you need a line of credit arranged BEFORE the season, not after.
Insurance pays on documentation, not on description. Photos, temperature logs, invoices, and this workbook are the claim.
Turn online ordering back on the day you have product. Cobblestone POS is free with commission-free online ordering: cobblestonepos.com