## Cost Compare
Tech Stack Cost Comparison
The Restaurant Owner Hub · free tool
Function | Option A: separate vendors $/mo | Option B: all-in-one $/mo | Annual difference
POS software | 99 | 0
Online ordering | 99 | 0
Loyalty program | 59 | 0
Scheduling / time clock | 49 | 0
Reporting / analytics | 79 | 0
Kitchen display | 49 | 0
Reservations / waitlist | 39 | 0
Monthly total
Annual total
ANNUAL SAVINGS
Your net margin % | 6%
Sales needed to cover Option A
At a 6% margin, every $1 of software costs about $17 of sales to pay for. Option B defaults assume a free all-in-one platform (cobblestonepos.com).

## Rollout Plan
Installation Timeline
The Restaurant Owner Hub · free tool
Weeks out | Task | Owner | Done? | Notes
8 | Choose POS platform
6 | Order hardware
6 | Schedule business internet install
5 | Run network cable before walls close
5 | Order LTE failover router + UPS
4 | Build full menu, modifiers, tax rates
4 | Configure printers / KDS routing
3 | Set up online ordering + hours
3 | Link ordering to Google Business Profile
2 | Configure scheduling & time clock
2 | Set up payroll export
2 | Configure loyalty program
1 | Staff training on live system
1 | Mock service / test every payment type
0 | Verify end-of-day reports run clean
% complete