## POS Migration
POS Migration Checklist
The Restaurant Owner Hub · free tool
Task | Target date | Done? | Owner
Export menu, prices & tax settings | Wk -4
Export customer / loyalty lists | Wk -4
Export sales history for accounting | Wk -4
Order hardware & pick go-live date | Wk -3
Rebuild menu, modifiers, prices | Wk -2
Set up employee logins & permissions | Wk -2
Test-ring complex orders & splits | Wk -2
Train staff in training mode | Wk -1
Print role cheat sheets | Wk -1
Go live on a SLOW day | Go-live
Keep old system on standby 1-2 days | Go-live
Debrief & fix menu buttons | Wk +1
Work top to bottom over ~4 weeks. Nothing important should happen for the first time during live service - go live on a Tuesday, not a Friday.