## Marketing Checklist
Pre-Opening Marketing Checklist
The Restaurant Owner Hub · free tool
Task | When | Owner | Done ✓
Claim Google Business Profile | 6 weeks out | Owner
Set up Instagram + Facebook | 6 weeks out | Owner
Launch website with menu & hours | 5 weeks out | Owner
Set up online ordering (Cobblestone) | 5 weeks out | Manager
Claim Yelp & review listings | 5 weeks out | Owner
Hang 'opening soon' banner on building | 4 weeks out | Manager
Post build-out / behind-the-scenes content | weekly | Owner
Start email signup for opening updates | 4 weeks out | Manager
Enroll loyalty program in POS | 3 weeks out | Manager
Host soft opening (friends/family/press) | 1 week out | Owner
Announce grand opening date everywhere | 1 week out | Owner
Pitch local food writers / neighborhood pages | 1 week out | Owner
Confirm staffing & inventory for the rush | opening week | Manager
Grand opening day | opening day | All
Work top to bottom. The build-out weeks are your cheapest marketing - use them. Capture every opening guest into loyalty + email for the second visit.