## 90-Day Plan
90-Day Opening Roadmap
The Restaurant Owner Hub · free tool
Week | Priority | Owner | Done? | Notes
1 | Execute the menu consistently; nightly debriefs
1 | Fix ticket times and station layout issues
2 | Tighten prep lists and par levels
2 | First inventory count
3 | Calculate first real food cost %
3 | Respond to every review; push loyalty signups
4 | First month-end close vs. projections
5 | Establish Monday numbers meeting
6 | Second inventory count; compare variance
7 | Address staffing: who stays, who goes
8 | Begin cross-training key positions
9 | Run menu profitability analysis
10 | Cut bottom items; reprice top sellers
11 | Rebuild schedule from real daypart data
11 | Renegotiate vendor pricing and terms
12 | Promote/hire a manager; hand off a shift
12 | Launch slow-daypart promotion
13 | 90-day review vs. original projections
% complete

## Weekly KPIs
Weekly KPI Tracker
The Restaurant Owner Hub · free tool
Week | Net sales $ | Food cost $ | Labor cost $ | Covers | Food % | Labor % | Prime % | Avg check $ | Flag
1
2
3
4
5
6
7
8
9
10
11
12
13
13-week average prime cost
Prime cost over 65% for three straight weeks is an emergency, not a trend. Pull these numbers from your POS every Monday.